## Sheet1
Task Management
No | Milestone Task | Is Milestone | Responsible | Plan Start | Plan Duration | Plan End | Actual Start | Actual Duration | Actual End | Actual Progress | Status | Complexity | Priority | Flag | Plan Hour | Actual Hour | Heattasks | Remarks | #
1 | Design & Development | Yes | Abitama | 2025-11-05 | 6 | 2025-11-11 | 2025-11-06 | 7 | 2025-11-13 | 100% | Open | T0 | Low | True | 100 | 110 | 14.3 | 1. ada ng 2. ada lagi 3 ada lagi
2 | Technical Spec & Kickoff | Yes | Lutfillah Amin
3 | 3D Drawing | No | Abitama
4 | FEA Analysis IT13 | Yes | Lutfillah Amin
5 | FEA Analysis MLT & DT | Yes
6 | Drawing 2D
7 | Drawing 2D Approval
8 | 3D mold design
9 | Casting simulation
10 | Reporting Simulasi
11 | 3D Mold Manufaktur | No
12 | Mold Drawing for Manufacturing
13 | Mold Drawing Approval
14 | Machining tooling design
15 | PR/PO Mold, Tool, & Jig
16 | Mold & Tooling Procurement
17 | Mold manufacture (#1)
18 | Machining tooling manufacture
19 | Trial Preparation Casting
20 | Trial Preparation Machining
21 | Process & Development | Yes
22 | Engineering Trial Casting T0
23 | Engineering Trial Machining T0
24 | Engineering Trial Painting T0
25 | Mold modification
26 | Strength test evaluation T0
27 | Engineering Trial Casting T1
28 | Engineering Trial Machining T1
29 | Engineering Trial Painting T1
30 | Strength test evaluation T1
31 | Paint Performance test evaluation
33 | Received master color
34 | Color matching | Yes
35 | Approval colour
36 | Packaging Preparation
37 | Packaging Trial dan Standard
38 | Packaging Preparaton
40 | Part Inspection Standard
41 | QC Process Chart
42 | Standard Operational Procedure & WI Casting
43 | Standard Operational Procedure & WI Machining
44 | Standard Operational Procedure & WI Painting
45 | Bill of Material Casting
46 | Bill of Material Machining
47 | Bill of Material Painting
48 | PFMEA Casting
49 | PFMEA Machining | Yes | Abitama | 2025-11-09 | 5 | 2025-11-14 | 2025-11-16 | 2 | 2025-11-18 | 90% | In progress | Design planning | Medium | True | 1 | 5 | 0.5 | ghkgffu
50 | PFMEA Painting | No | Lutfillah Amin | 2025-11-06 | 5 | 2025-11-11 | 2025-11-06 | 2 | 2025-11-08 | 45% | Open | Tooling mtg
51 | Massproduction Preparation
52 | Customer Audit