## Sheet1
Task Management
No | Milestone Task | Is Milestone | Responsible | Plan Start | Plan Duration | Plan End | Actual Start | Actual Duration | Actual End | Actual Progress | Status | Complexity | Priority | Flag | Plan Hour | Actual Hour | Heattasks | Remarks | #
1 | Design & Development | Yes | Lutfillah Amin
2 | Technical Spec & Kickoff
3 | 3D Drawing | No | Abitama | 2025-11-04 | 2 | 2025-11-06 | 2025-10-31 | 2 | 2025-11-02 | 55% | In progress | Design planning | Low | True | 5 | 10 | 2.5 | coba
4 | FEA Analysis IT13
5 | FEA Analysis MLT & DT
6 | Drawing 2D
7 | Drawing 2D Approval
8 | 3D mold design | Yes | Lutfillah Amin | 2025-10-31 | 3 | 2025-11-03 | 2025-11-01 | 7 | 2025-11-08 | 5% | In progress | Tooling mtg | Low | True | 6 | 2 | 0.9 | catatan2
9 | Casting simulation
10 | Reporting Simulasi
11 | 3D Mold Manufaktur | Yes |  | 2025-11-02 | 7 | 2025-11-09 | 2025-11-01 | 10 | 2025-11-11 | 55% | Cancelled |  | Medium |  | 5 | 4 | 0.5
12 | Mold Drawing for Manufacturing
13 | Mold Drawing Approval
14 | Machining tooling design
15 | PR/PO Mold, Tool, & Jig
16 | Mold & Tooling Procurement
17 | Mold manufacture (#1)
18 | Machining tooling manufacture
19 | Trial Preparation Casting
20 | Trial Preparation Machining | Yes | Abitama | 2025-11-06 | 5 | 2025-11-11 | 2025-11-05 | 6 | 2025-11-11 | [5 empty] | 3 |  | 0.5
21 | Process & Development
22 | Engineering Trial Casting T0
23 | Engineering Trial Machining T0
24 | Engineering Trial Painting T0
25 | Mold modification
26 | Strength test evaluation T0
27 | Engineering Trial Casting T1
28 | Engineering Trial Machining T1
29 | Engineering Trial Painting T1
30 | Strength test evaluation T1
31 | Paint Performance test evaluation
32 | New Paint Color Development
33 | Received master color
34 | Color matching
35 | Approval colour | Yes | Lutfillah Amin | 2025-11-11 | 5 | 2025-11-16 | 2025-11-03 | 3 | 2025-11-06 | 65% | Completed | IPC | Low | True | 2 | 2 | 0.7 | agjkhgiagiug uyuaygaBDJKSBAKJKhuhGjh
36 | Packaging Preparation
37 | Packaging Trial dan Standard
38 | Packaging Preparaton
39 | Document Preparation
40 | Part Inspection Standard
41 | QC Process Chart
42 | Standard Operational Procedure & WI Casting
43 | Standard Operational Procedure & WI Machining
44 | Standard Operational Procedure & WI Painting
45 | Bill of Material Casting | No | Abitama | [6 empty] | 80%
46 | Bill of Material Machining | Yes | Lutfillah Amin | 2025-11-05 | 5 | 2025-11-10 | 2025-11-06 | 5 | 2025-11-11 | 0% | In progress | Masspro | Medium | True | 2 | 6 | 0.4
47 | Bill of Material Painting | [8 empty] | 10% |  |  |  |  | 2 | 8
48 | PFMEA Casting
49 | PFMEA Machining
50 | PFMEA Painting
51 | Massproduction Preparation
52 | Pre mass production preparation audit
53 | PPAP/ISIR
54 | Customer Audit
55 | ALC Code | Yes |  | 2025-11-01 | 2 | 2025-11-03 | 2025-10-31 | 1 | 2025-11-01 | 70% | Completed |  |  |  | 5 | 2 | 5
56 | Mass Production Readiness