## Sheet1
Task Management
Milestone Task | Is Milestone | Responsible | Plan Start | Plan Duration | Plan End | Actual Start | Actual Duration | Actual End | Actual Progress | Status | Complexity | Priority | Flag | Plan Hour | Actual Hour
3D Drawing | Yes | Abitama | 2025-10-30 | 7 | 2025-11-06 | 2025-10-30 | 6 | 2025-11-05 | 10% | In progress | Design planning | Low | True | 5 | 6
3D mold design |  | Lutfillah Amin | 2025-10-31 | 3 | 2025-11-03 | 2025-11-01 | 7 | 2025-11-08 | 90% | In progress
3D Mold Manufaktur |  |  | 2025-11-02 | 7 | 2025-11-09 | 2025-11-01 | 10 | 2025-11-11 | [5 empty] | 5 | 4
ALC Code |  |  | 2025-11-01 | 2 | 2025-11-03 | 2025-10-31 | 1 | 2025-11-01 | [5 empty] | 4
Approval colour
Bill of Material Casting
Bill of Material Machining
Bill of Material Painting
Casting simulation
Color matching
Customer Audit
Design & Development
Document Preparation
Drawing 2D
Drawing 2D Approval
Engineering Trial Casting T0
Engineering Trial Casting T1
Engineering Trial Machining T0
Engineering Trial Machining T1
Engineering Trial Painting T0
Engineering Trial Painting T1
FEA Analysis IT13
FEA Analysis MLT & DT
Machining tooling design
Machining tooling manufacture
Mass Production Readiness
Massproduction Preparation
Mold & Tooling Procurement
Mold Drawing Approval
Mold Drawing for Manufacturing
Mold manufacture (#1)
Mold modification
New Paint Color Development
Packaging Preparation
Packaging Preparaton
Packaging Trial dan Standard
Paint Performance test evaluation
Part Inspection Standard
PFMEA Casting
PFMEA Machining
PFMEA Painting
PPAP/ISIR
PR/PO Mold, Tool, & Jig
Pre mass production preparation audit
Process & Development
QC Process Chart
Received master color
Reporting Simulasi
Standard Operational Procedure & WI Casting
Standard Operational Procedure & WI Machining
Standard Operational Procedure & WI Painting
Strength test evaluation T0
Strength test evaluation T1
Technical Spec & Kickoff
Trial Preparation Casting
Trial Preparation Machining